## Dashboard
Project Ticketing
Dashboard
Upcoming |  |  |  | Project Plan
Issue | Owner | Open Date
Keyboard scanner won't open up | Bruce Wayne | 2022-12-31
Server email folder not responding | Harley Quinn | 2022-12-31
Keyboard scanner not responding | Joker | 2022-12-31
Keyboard scanner won't open up | Alfred Pennyworth | 2022-12-31
Keyboard scanner not responding | Richard Grayson | 2022-12-31
Missing monitoring meter | Lucius Fox | 2022-12-31
Project % Tracker | 12% | 0.12
People
Names | Issues |  | Activities
Status
days to go
activities on-going
active issues
101
70
23
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Data
People & Task Data
2022-10-31
Person | Team | Activity | Category | Owner | Start Date | End Date | % Done
Bruce Wayne | Baahu | Act 001 | Design | Barbara Gordon | 2022-08-01 | 2022-11-04 | 59% | 2021-03-01 | 2021-03-04 | 2023-03-01 | 2023-03-04
James Gordon | Baahu | Act 002 | Deployment | Harley Quinn | 2022-08-01 | 2022-11-11 | 70% | 2021-03-01 | 2021-03-11 | 2023-03-01 | 2023-03-11
Alfred Pennyworth | Baahu | Act 003 | Requirements | Richard Grayson | 2022-08-03 | 2022-11-07 | 62% | 2021-03-03 | 2021-03-07 | 2023-03-03 | 2023-03-07
Bane | Baahu | Act 004 | Requirements | Selina Kyle | 2022-08-04 | 2022-11-14 | 60% | 2021-03-04 | 2021-03-14 | 2023-03-04 | 2023-03-14
Selina Kyle | Baahu | Act 005 | Design | Richard Grayson | 2022-08-05 | 2022-11-12 | 75% | 2021-03-05 | 2021-03-12 | 2023-03-05 | 2023-03-12
Harley Quinn | Bhalla | Act 006 | Design | Bruce Wayne | 2022-08-06 | 2022-11-16 | 100% | 2021-03-06 | 2021-03-16 | 2023-03-06 | 2023-03-16
Barbara Gordon | Bhalla | Act 007 | Development | Barbara Gordon | 2022-08-07 | 2022-11-15 | 78% | 2021-03-07 | 2021-03-15 | 2023-03-07 | 2023-03-15
Richard Grayson | Bhalla | Act 008 | Testing | Barbara Gordon | 2022-08-07 | 2022-11-16 | 61% | 2021-03-07 | 2021-03-16 | 2023-03-07 | 2023-03-16
Joker | Bhalla | Act 009 | Requirements | Alfred Pennyworth | 2022-08-07 | 2022-11-11 | 100% | 2021-03-07 | 2021-03-11 | 2023-03-07 | 2023-03-11
Lucius Fox | Bhalla | Act 010 | Requirements | Alfred Pennyworth | 2022-08-08 | 2022-11-13 | 27% | 2021-03-08 | 2021-03-13 | 2023-03-08 | 2023-03-13
|  | Act 011 | Development | Selina Kyle | 2022-08-08 | 2022-11-18 | 100% | 2021-03-08 | 2021-03-18 | 2023-03-08 | 2023-03-18
|  | Act 012 | Deployment | Joker | 2022-08-08 | 2022-11-14 | 88% | 2021-03-08 | 2021-03-14 | 2023-03-08 | 2023-03-14
|  | Act 013 | Design | Lucius Fox | 2022-08-09 | 2022-11-13 | 51% | 2021-03-09 | 2021-03-13 | 2023-03-09 | 2023-03-13
|  | Act 014 | Requirements | Harley Quinn | 2022-08-11 | 2022-11-15 | 95% | 2021-03-11 | 2021-03-15 | 2023-03-11 | 2023-03-15
|  | Act 015 | Testing | Bane | 2022-08-13 | 2022-11-23 | 70% | 2021-03-13 | 2021-03-23 | 2023-03-13 | 2023-03-23
|  | Act 016 | Deployment | Selina Kyle | 2022-08-13 | 2022-11-19 | 99% | 2021-03-13 | 2021-03-19 | 2023-03-13 | 2023-03-19
|  | Act 017 | Development | Barbara Gordon | 2022-08-15 | 2022-11-19 | 100% | 2021-03-15 | 2021-03-19 | 2023-03-15 | 2023-03-19
|  | Act 018 | Requirements | Harley Quinn | 2022-08-16 | 2022-11-22 | 100% | 2021-03-16 | 2021-03-22 | 2023-03-16 | 2023-03-22
|  | Act 019 | Deployment | Joker | 2022-08-17 | 2022-11-22 | 100% | 2021-03-17 | 2021-03-22 | 2023-03-17 | 2023-03-22
|  | Act 020 | Requirements | Alfred Pennyworth | 2022-08-18 | 2022-11-24 | 83% | 2021-03-18 | 2021-03-24 | 2023-03-18 | 2023-03-24
|  | Act 021 | Development | Alfred Pennyworth | 2022-08-18 | 2022-11-23 | 100% | 2021-03-18 | 2021-03-23 | 2023-03-18 | 2023-03-23
|  | Act 022 | Deployment | Harley Quinn | 2022-08-18 | 2022-11-21 | 44% | 2021-03-18 | 2021-03-21 | 2023-03-18 | 2023-03-21
|  | Act 023 | Development | James Gordon | 2022-08-19 | 2022-11-26 | 100% | 2021-03-19 | 2021-03-26 | 2023-03-19 | 2023-03-26
|  | Act 024 | Testing | Lucius Fox | 2022-08-19 | 2022-11-24 | 88% | 2021-03-19 | 2021-03-24 | 2023-03-19 | 2023-03-24
|  | Act 025 | Deployment | James Gordon | 2022-08-21 | 2022-11-25 | 100% | 2021-03-21 | 2021-03-25 | 2023-03-21 | 2023-03-25
|  | Act 026 | Testing | Selina Kyle | 2022-08-23 | 2022-11-30 | 70% | 2021-03-23 | 2021-03-30 | 2023-03-23 | 2023-03-30
|  | Act 027 | Deployment | James Gordon | 2022-08-24 | 2022-11-28 | 100% | 2021-03-24 | 2021-03-28 | 2023-03-24 | 2023-03-28
|  | Act 028 | Deployment | Bane | 2022-08-24 | 2022-12-02 | 79% | 2021-03-24 | 2021-04-02 | 2023-03-24 | 2023-04-02
|  | Act 029 | Testing | Bruce Wayne | 2022-08-25 | 2022-11-30 | 100% | 2021-03-25 | 2021-03-31 | 2023-03-25 | 2023-03-31
|  | Act 030 | Testing | Richard Grayson | 2022-08-27 | 2022-12-04 | 100% | 2021-03-27 | 2021-04-04 | 2023-03-27 | 2023-04-04
|  | Act 031 | Development | Bane | 2022-08-27 | 2022-12-06 | 76% | 2021-03-27 | 2021-04-06 | 2023-03-27 | 2023-04-06
|  | Act 032 | Deployment | Joker | 2022-08-29 | 2022-12-02 | 22% | 2021-03-29 | 2021-04-02 | 2023-03-29 | 2023-04-02
|  | Act 033 | Testing | Alfred Pennyworth | 2022-08-29 | 2022-12-04 | 67% | 2021-03-29 | 2021-04-04 | 2023-03-29 | 2023-04-04
|  | Act 034 | Requirements | Selina Kyle | 2022-08-29 | 2022-12-06 | 100% | 2021-03-29 | 2021-04-06 | 2023-03-29 | 2023-04-06
|  | Act 035 | Requirements | James Gordon | 2022-08-29 | 2022-12-06 | 100% | 2021-03-29 | 2021-04-06 | 2023-03-29 | 2023-04-06
|  | Act 036 | Development | Bane | 2022-08-30 | 2022-12-07 | 100% | 2021-03-30 | 2021-04-07 | 2023-03-30 | 2023-04-07
|  | Act 037 | Requirements | Richard Grayson | 2022-09-01 | 2022-12-04 | 100% | 2021-04-01 | 2021-04-04 | 2023-04-01 | 2023-04-04
|  | Act 038 | Deployment | Bane | 2022-09-02 | 2022-12-05 | 100% | 2021-04-02 | 2021-04-05 | 2023-04-02 | 2023-04-05
|  | Act 039 | Design | Lucius Fox | 2022-09-03 | 2022-12-09 | 100% | 2021-04-03 | 2021-04-09 | 2023-04-03 | 2023-04-09
|  | Act 040 | Requirements | Lucius Fox | 2022-09-03 | 2022-12-11 | 27% | 2021-04-03 | 2021-04-11 | 2023-04-03 | 2023-04-11
|  | Act 041 | Design | Richard Grayson | 2022-09-03 | 2022-12-06 | 100% | 2021-04-03 | 2021-04-06 | 2023-04-03 | 2023-04-06
|  | Act 042 | Testing | James Gordon | 2022-09-03 | 2022-12-09 | 100% | 2021-04-03 | 2021-04-09 | 2023-04-03 | 2023-04-09
|  | Act 043 | Requirements | Barbara Gordon | 2022-09-05 | 2022-12-11 | 84% | 2021-04-05 | 2021-04-11 | 2023-04-05 | 2023-04-11
|  | Act 044 | Deployment | Richard Grayson | 2022-09-07 | 2022-12-15 | 45% | 2021-04-07 | 2021-04-15 | 2023-04-07 | 2023-04-15
|  | Act 045 | Development | Bruce Wayne | 2022-09-08 | 2022-12-14 | 92% | 2021-04-08 | 2021-04-14 | 2023-04-08 | 2023-04-14
|  | Act 046 | Testing | Bane | 2022-09-09 | 2022-12-19 | 66% | 2021-04-09 | 2021-04-19 | 2023-04-09 | 2023-04-19
|  | Act 047 | Design | James Gordon | 2022-09-10 | 2022-12-13 | 65% | 2021-04-10 | 2021-04-13 | 2023-04-10 | 2023-04-13
|  | Act 048 | Requirements | Bruce Wayne | 2022-09-11 | 2022-12-15 | 100% | 2021-04-11 | 2021-04-15 | 2023-04-11 | 2023-04-15
|  | Act 049 | Deployment | Barbara Gordon | 2022-09-13 | 2022-12-19 | 79% | 2021-04-13 | 2021-04-19 | 2023-04-13 | 2023-04-19
|  | Act 050 | Design | Joker | 2022-09-14 | 2022-12-23 | 100% | 2021-04-14 | 2021-04-23 | 2023-04-14 | 2023-04-23
|  | Act 051 | Testing | Alfred Pennyworth | 2022-09-15 | 2022-12-22 | 96% | 2021-04-15 | 2021-04-22 | 2023-04-15 | 2023-04-22
|  | Act 052 | Design | Bruce Wayne | 2022-09-17 | 2022-12-23 | 100% | 2021-04-17 | 2021-04-23 | 2023-04-17 | 2023-04-23
|  | Act 053 | Design | Lucius Fox | 2022-09-19 | 2022-12-24 | 59% | 2021-04-19 | 2021-04-24 | 2023-04-19 | 2023-04-24
|  | Act 054 | Development | Barbara Gordon | 2022-09-21 | 2022-12-27 | 100% | 2021-04-21 | 2021-04-27 | 2023-04-21 | 2023-04-27
|  | Act 055 | Testing | Barbara Gordon | 2022-09-23 | 2022-12-26 | 21% | 2021-04-23 | 2021-04-26 | 2023-04-23 | 2023-04-26
|  | Act 056 | Requirements | Joker | 2022-09-25 | 2022-12-29 | 96% | 2021-04-25 | 2021-04-29 | 2023-04-25 | 2023-04-29
|  | Act 057 | Design | Alfred Pennyworth | 2022-09-25 | 2023-01-04 | 62% | 2021-04-25 | 2021-05-04 | 2023-04-25 | 2023-05-04
|  | Act 058 | Development | Selina Kyle | 2022-09-25 | 2023-01-01 | 72% | 2021-04-25 | 2021-05-01 | 2023-04-25 | 2023-05-01
|  | Act 059 | Development | Harley Quinn | 2022-09-25 | 2023-01-01 | 45% | 2021-04-25 | 2021-05-01 | 2023-04-25 | 2023-05-01
|  | Act 060 | Deployment | Richard Grayson | 2022-09-26 | 2023-01-06 | 25% | 2021-04-26 | 2021-05-06 | 2023-04-26 | 2023-05-06
|  | Act 061 | Requirements | James Gordon | 2022-09-28 | 2023-01-03 | 87% | 2021-04-28 | 2021-05-03 | 2023-04-28 | 2023-05-03
|  | Act 062 | Design | Bane | 2022-09-30 | 2023-01-08 | 100% | 2021-04-30 | 2021-05-08 | 2023-04-30 | 2023-05-08
|  | Act 063 | Development | Lucius Fox | 2022-09-30 | 2023-01-03 | 0% | 2021-04-30 | 2021-05-03 | 2023-04-30 | 2023-05-03
|  | Act 064 | Design | Lucius Fox | 2022-10-01 | 2023-01-09 | 0% | 2021-05-01 | 2021-05-09 | 2023-05-01 | 2023-05-09
|  | Act 065 | Development | Alfred Pennyworth | 2022-10-01 | 2023-01-08 | 0% | 2021-05-01 | 2021-05-08 | 2023-05-01 | 2023-05-08
|  | Act 066 | Testing | Richard Grayson | 2022-10-02 | 2023-01-06 | 0% | 2021-05-02 | 2021-05-06 | 2023-05-02 | 2023-05-06
|  | Act 067 | Requirements | Barbara Gordon | 2022-10-02 | 2023-01-10 | 0% | 2021-05-02 | 2021-05-10 | 2023-05-02 | 2023-05-10
|  | Act 068 | Deployment | Joker | 2022-10-04 | 2023-01-13 | 0% | 2021-05-04 | 2021-05-13 | 2023-05-04 | 2023-05-13
|  | Act 069 | Deployment | Joker | 2022-10-05 | 2023-01-12 | 0% | 2021-05-05 | 2021-05-12 | 2023-05-05 | 2023-05-12
|  | Act 070 | Development | James Gordon | 2022-10-05 | 2023-01-08 | 0% | 2021-05-05 | 2021-05-08 | 2023-05-05 | 2023-05-08
|  | Act 071 | Design | Bruce Wayne | 2022-10-07 | 2023-01-12 | 0% | 2021-05-07 | 2021-05-12 | 2023-05-07 | 2023-05-12
|  | Act 072 | Requirements | Richard Grayson | 2022-10-07 | 2023-01-13 | 0% | 2021-05-07 | 2021-05-13 | 2023-05-07 | 2023-05-13
|  | Act 073 | Testing | Selina Kyle | 2022-10-09 | 2023-01-17 | 0% | 2021-05-09 | 2021-05-17 | 2023-05-09 | 2023-05-17
|  | Act 074 | Design | Bane | 2022-10-10 | 2023-01-20 | 0% | 2021-05-10 | 2021-05-20 | 2023-05-10 | 2023-05-20
|  | Act 075 | Deployment | Selina Kyle | 2022-10-11 | 2023-01-14 | 0% | 2021-05-11 | 2021-05-14 | 2023-05-11 | 2023-05-14
|  | Act 076 | Deployment | Barbara Gordon | 2022-10-12 | 2023-01-19 | 0% | 2021-05-12 | 2021-05-19 | 2023-05-12 | 2023-05-19
|  | Act 077 | Design | Richard Grayson | 2022-10-13 | 2023-01-20 | 0% | 2021-05-13 | 2021-05-20 | 2023-05-13 | 2023-05-20
|  | Act 078 | Requirements | Selina Kyle | 2022-10-13 | 2023-01-22 | 0% | 2021-05-13 | 2021-05-22 | 2023-05-13 | 2023-05-22
|  | Act 079 | Deployment | Barbara Gordon | 2022-10-14 | 2023-01-19 | 0% | 2021-05-14 | 2021-05-19 | 2023-05-14 | 2023-05-19
|  | Act 080 | Testing | Barbara Gordon | 2022-10-15 | 2023-01-21 | 0% | 2021-05-15 | 2021-05-21 | 2023-05-15 | 2023-05-21
|  | Act 081 | Design | Harley Quinn | 2022-10-16 | 2023-01-26 | 0% | 2021-05-16 | 2021-05-26 | 2023-05-16 | 2023-05-26
|  | Act 082 | Design | Richard Grayson | 2022-10-16 | 2023-01-20 | 0% | 2021-05-16 | 2021-05-20 | 2023-05-16 | 2023-05-20
|  | Act 083 | Development | Barbara Gordon | 2022-10-17 | 2023-01-25 | 0% | 2021-05-17 | 2021-05-25 | 2023-05-17 | 2023-05-25
|  | Act 084 | Requirements | Alfred Pennyworth | 2022-10-18 | 2023-01-26 | 0% | 2021-05-18 | 2021-05-26 | 2023-05-18 | 2023-05-26
|  | Act 085 | Development | James Gordon | 2022-10-18 | 2023-01-27 | 0% | 2021-05-18 | 2021-05-27 | 2023-05-18 | 2023-05-27
|  | Act 086 | Development | Richard Grayson | 2022-10-19 | 2023-01-27 | 0% | 2021-05-19 | 2021-05-27 | 2023-05-19 | 2023-05-27
|  | Act 087 | Requirements | Bane | 2022-10-20 | 2023-01-28 | 0% | 2021-05-20 | 2021-05-28 | 2023-05-20 | 2023-05-28
|  | Act 088 | Deployment | Bane | 2022-10-22 | 2023-01-26 | 0% | 2021-05-22 | 2021-05-26 | 2023-05-22 | 2023-05-26
|  | Act 089 | Testing | Lucius Fox | 2022-10-23 | 2023-01-26 | 0% | 2021-05-23 | 2021-05-26 | 2023-05-23 | 2023-05-26
|  | Act 090 | Requirements | Barbara Gordon | 2022-10-23 | 2023-01-28 | 0% | 2021-05-23 | 2021-05-28 | 2023-05-23 | 2023-05-28
|  | Act 091 | Design | Joker | 2022-10-25 | 2023-01-28 | 0% | 2021-05-25 | 2021-05-28 | 2023-05-25 | 2023-05-28
|  | Act 092 | Requirements | Bane | 2022-10-27 | 2023-02-05 | 0% | 2021-05-27 | 2021-06-05 | 2023-05-27 | 2023-06-05
|  | Act 093 | Requirements | James Gordon | 2022-10-29 | 2023-02-02 | 0% | 2021-05-29 | 2021-06-02 | 2023-05-29 | 2023-06-02
|  | Act 094 | Requirements | Lucius Fox | 2022-10-30 | 2023-02-03 | 0% | 2021-05-30 | 2021-06-03 | 2023-05-30 | 2023-06-03
|  | Act 095 | Requirements | Selina Kyle | 2022-10-31 | 2023-02-08 | 0% | 2021-05-31 | 2021-06-08 | 2023-05-31 | 2023-06-08
|  | Act 096 | Deployment | Barbara Gordon | 2022-11-01 | 2023-02-04 | 0% | 2021-06-01 | 2021-06-04 | 2023-06-01 | 2023-06-04
|  | Act 097 | Design | Lucius Fox | 2022-11-01 | 2023-02-04 | 0% | 2021-06-01 | 2021-06-04 | 2023-06-01 | 2023-06-04
|  | Act 098 | Testing | Lucius Fox | 2022-11-01 | 2023-02-09 | 0% | 2021-06-01 | 2021-06-09 | 2023-06-01 | 2023-06-09
|  | Act 099 | Design | Barbara Gordon | 2022-11-03 | 2023-02-06 | 0% | 2021-06-03 | 2021-06-06 | 2023-06-03 | 2023-06-06
|  | Act 100 | Requirements | James Gordon | 2022-11-05 | 2023-02-09 | 0% | 2021-06-05 | 2021-06-09 | 2023-06-05 | 2023-06-09

## Issues
Issue Tracker
Issue | Assigned to | Priority | Date opened | Date Closed
Keyboard scanner won't open up | Bruce Wayne | High | 2022-12-31 |  | 2021-04-02
Server email folder not responding | Harley Quinn | High | 2022-12-31 |  | 2021-04-03
Keyboard scanner not responding | Joker | High | 2022-12-31 |  | 2021-04-04
Keyboard scanner won't open up | Alfred Pennyworth | Low | 2022-12-31 | 2022-12-31 | 2021-04-05 | 2021-04-08
Keyboard scanner not responding | Richard Grayson | Low | 2022-12-31 |  | 2021-04-05
Missing monitoring meter | Lucius Fox | Low | 2022-12-31 |  | 2021-04-06
Server email folder are not working | Bruce Wayne | Low | 2022-12-31 |  | 2021-04-07
User specifications are not working | James Gordon | Low | 2022-12-31 |  | 2021-04-07
Missing interaction effects | Joker | High | 2022-12-31 |  | 2021-04-08
Battery status screen not responding | Selina Kyle | High | 2022-12-31 |  | 2021-04-09
Broken template files | Lucius Fox | Low | 2022-12-31 | 2022-12-31 | 2021-04-11 | 2021-04-14
Closed template files | Harley Quinn | Low | 2022-12-31 |  | 2021-04-12
Keyboard scanner won't open up | James Gordon | Low | 2022-12-31 |  | 2021-04-14
User specifications is blended | Joker | Low | 2022-12-31 |  | 2021-04-17
Missing interaction effects | Alfred Pennyworth | High | 2022-12-31 |  | 2021-04-17
Closed expansion slots | Lucius Fox | High | 2022-12-31 |  | 2021-04-18
Missing template files | James Gordon | Low | 2022-12-31 |  | 2021-04-19
Closed expansion slots | Lucius Fox | Low | 2022-12-31 |  | 2021-04-19
Battery status screen are not working | Bruce Wayne | Low | 2022-12-31 |  | 2021-04-20
Closed monitoring meter | Joker | Low | 2022-12-31 |  | 2021-04-22
Closed expansion slots | Barbara Gordon | Low | 2022-12-31 |  | 2021-04-25
Broken expansion slots | James Gordon | High | 2022-12-31 |  | 2021-04-26
Missing expansion slots | Bane | High | 2022-12-31 |  | 2021-04-27
Slow template files | Richard Grayson | Low | 2022-12-31 |  | 2021-04-28
Broken template files | James Gordon | High | 2022-12-31 |  | 2021-04-30

## Calculation
Category | Activity | Min of Start Date | Max of End Date
Deployment |  | 2022-08-01 | 2022-12-04 | Start date | 2022-10-17
| Act 002 | 2022-08-01 | 2022-09-11 | Current Date | 2022-10-31
| Act 012 | 2022-08-08 | 2022-09-14 | Choices | 2
| Act 016 | 2022-08-13 | 2022-09-19 | Activities
| Act 019 | 2022-08-17 | 2022-09-22 | Issues
| Act 022 | 2022-08-18 | 2022-09-21
| Act 025 | 2022-08-21 | 2022-09-25
| Act 027 | 2022-08-24 | 2022-09-28 | Upcoming Activities |  |  | Dashboard Cndition |  |  | Row Labels | Count of Assigned to | Count of Activity
| Act 028 | 2022-08-24 | 2022-10-02 | [6 empty] | Alfred Pennyworth | 2 | 9
| Act 032 | 2022-08-29 | 2022-10-02 | Activity | Category | Start Date | Issue | Owner | Open Date | Bane | 1 | 11
| Act 038 | 2022-09-02 | 2022-10-05 | Act 096 | Deployment | 2022-11-01 | Keyboard scanner won't open up | Bruce Wayne | 44926 | Barbara Gordon | 1 | 16
| Act 044 | 2022-09-07 | 2022-10-15 | Act 097 | Design | 2022-11-01 | Server email folder not responding | Harley Quinn | 44926 | Bruce Wayne | 3 | 6
| Act 049 | 2022-09-13 | 2022-10-19 | Act 098 | Testing | 2022-11-01 | Keyboard scanner not responding | Joker | 44926 | Harley Quinn | 2 | 6
| Act 060 | 2022-09-26 | 2022-11-06 | Act 099 | Design | 2022-11-03 | Keyboard scanner won't open up | Alfred Pennyworth | 44926 | James Gordon | 5 | 11
| Act 068 | 2022-10-04 | 2022-11-13 | Act 100 | Requirements | 2022-11-05 | Keyboard scanner not responding | Richard Grayson | 44926 | Joker | 4 | 8
| Act 069 | 2022-10-05 | 2022-11-12 |  |  |  | Missing monitoring meter | Lucius Fox | 44926 | Lucius Fox | 4 | 11
| Act 075 | 2022-10-11 | 2022-11-14 | [6 empty] | Richard Grayson | 2 | 12
| Act 076 | 2022-10-12 | 2022-11-19 | [6 empty] | Selina Kyle | 1 | 10
| Act 079 | 2022-10-14 | 2022-11-19
| Act 088 | 2022-10-22 | 2022-11-26 | Upcoming Issues
| Act 096 | 2022-11-01 | 2022-12-04
Design |  | 2022-08-01 | 2022-12-06 | Issue | Owner | Open Date
| Act 001 | 2022-08-01 | 2022-09-04 | Keyboard scanner won't open up | Bruce Wayne | 2022-12-31
| Act 005 | 2022-08-05 | 2022-09-12 | Server email folder not responding | Harley Quinn | 2022-12-31
| Act 006 | 2022-08-06 | 2022-09-16 | Keyboard scanner not responding | Joker | 2022-12-31
| Act 013 | 2022-08-09 | 2022-09-13 | Keyboard scanner won't open up | Alfred Pennyworth | 2022-12-31
| Act 039 | 2022-09-03 | 2022-10-09 | Keyboard scanner not responding | Richard Grayson | 2022-12-31
| Act 041 | 2022-09-03 | 2022-10-06 | Missing monitoring meter | Lucius Fox | 2022-12-31
| Act 047 | 2022-09-10 | 2022-10-13
| Act 050 | 2022-09-14 | 2022-10-23
| Act 052 | 2022-09-17 | 2022-10-23
| Act 053 | 2022-09-19 | 2022-10-24 | Dashboard tiles calculations
| Act 057 | 2022-09-25 | 2022-11-04
| Act 062 | 2022-09-30 | 2022-11-08 | Days Left | 101
| Act 064 | 2022-10-01 | 2022-11-09
| Act 071 | 2022-10-07 | 2022-11-12 | On-going | 70
| Act 074 | 2022-10-10 | 2022-11-20
| Act 077 | 2022-10-13 | 2022-11-20 | Active issues | 23
| Act 081 | 2022-10-16 | 2022-11-26
| Act 082 | 2022-10-16 | 2022-11-20
| Act 091 | 2022-10-25 | 2022-11-28
| Act 097 | 2022-11-01 | 2022-12-04
| Act 099 | 2022-11-03 | 2022-12-06
Development |  | 2022-08-07 | 2022-11-27
| Act 007 | 2022-08-07 | 2022-09-15
| Act 011 | 2022-08-08 | 2022-09-18
| Act 017 | 2022-08-15 | 2022-09-19
| Act 021 | 2022-08-18 | 2022-09-23
| Act 023 | 2022-08-19 | 2022-09-26
| Act 031 | 2022-08-27 | 2022-10-06
| Act 036 | 2022-08-30 | 2022-10-07
| Act 045 | 2022-09-08 | 2022-10-14
| Act 054 | 2022-09-21 | 2022-10-27
| Act 058 | 2022-09-25 | 2022-11-01
| Act 059 | 2022-09-25 | 2022-11-01
| Act 063 | 2022-09-30 | 2022-11-03
| Act 065 | 2022-10-01 | 2022-11-08
| Act 070 | 2022-10-05 | 2022-11-08
| Act 083 | 2022-10-17 | 2022-11-25
| Act 085 | 2022-10-18 | 2022-11-27
| Act 086 | 2022-10-19 | 2022-11-27
Requirements |  | 2022-08-03 | 2022-12-09
| Act 003 | 2022-08-03 | 2022-09-07
| Act 004 | 2022-08-04 | 2022-09-14
| Act 009 | 2022-08-07 | 2022-09-11
| Act 010 | 2022-08-08 | 2022-09-13
| Act 014 | 2022-08-11 | 2022-09-15
| Act 018 | 2022-08-16 | 2022-09-22
| Act 020 | 2022-08-18 | 2022-09-24
| Act 034 | 2022-08-29 | 2022-10-06
| Act 035 | 2022-08-29 | 2022-10-06
| Act 037 | 2022-09-01 | 2022-10-04
| Act 040 | 2022-09-03 | 2022-10-11
| Act 043 | 2022-09-05 | 2022-10-11
| Act 048 | 2022-09-11 | 2022-10-15
| Act 056 | 2022-09-25 | 2022-10-29
| Act 061 | 2022-09-28 | 2022-11-03
| Act 067 | 2022-10-02 | 2022-11-10
| Act 072 | 2022-10-07 | 2022-11-13
| Act 078 | 2022-10-13 | 2022-11-22
| Act 084 | 2022-10-18 | 2022-11-26
| Act 087 | 2022-10-20 | 2022-11-28
| Act 090 | 2022-10-23 | 2022-11-28
| Act 092 | 2022-10-27 | 2022-12-05
| Act 093 | 2022-10-29 | 2022-12-02
| Act 094 | 2022-10-30 | 2022-12-03
| Act 095 | 2022-10-31 | 2022-12-08
| Act 100 | 2022-11-05 | 2022-12-09
Testing |  | 2022-08-07 | 2022-12-09
| Act 008 | 2022-08-07 | 2022-09-16
| Act 015 | 2022-08-13 | 2022-09-23
| Act 024 | 2022-08-19 | 2022-09-24
| Act 026 | 2022-08-23 | 2022-09-30
| Act 029 | 2022-08-25 | 2022-09-30
| Act 030 | 2022-08-27 | 2022-10-04
| Act 033 | 2022-08-29 | 2022-10-04
| Act 042 | 2022-09-03 | 2022-10-09
| Act 046 | 2022-09-09 | 2022-10-19
| Act 051 | 2022-09-15 | 2022-10-22
| Act 055 | 2022-09-23 | 2022-10-26
| Act 066 | 2022-10-02 | 2022-11-06
| Act 073 | 2022-10-09 | 2022-11-17
| Act 080 | 2022-10-15 | 2022-11-21
| Act 089 | 2022-10-23 | 2022-11-26
| Act 098 | 2022-11-01 | 2022-12-09
Grand Total |  | 2022-08-01 | 2022-12-09

## Gantt Chart
 | time axis 2022-10-17 to 2022-12-15
 | time axis 2022-10-17 to 2022-12-15
 | time axis 2022-10-17 to 2022-12-15
Category | Activity | Person | Start | End | %
Deployment |  |  | 2022-08-01 | 2022-12-04 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 002 | Harley Quinn | 2022-08-01 | 2022-09-11 | 70% | 70% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 012 | Joker | 2022-08-08 | 2022-09-14 | 88% | 88% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 016 | Selina Kyle | 2022-08-13 | 2022-09-19 | 99% | 99% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 019 | Joker | 2022-08-17 | 2022-09-22 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 022 | Harley Quinn | 2022-08-18 | 2022-09-21 | 44% | 44% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 025 | James Gordon | 2022-08-21 | 2022-09-25 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 027 | James Gordon | 2022-08-24 | 2022-09-28 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 028 | Bane | 2022-08-24 | 2022-10-02 | 79% | 79% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 032 | Joker | 2022-08-29 | 2022-10-02 | 22% | 22% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 038 | Bane | 2022-09-02 | 2022-10-05 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 044 | Richard Grayson | 2022-09-07 | 2022-10-15 | 45% | 45% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 049 | Barbara Gordon | 2022-09-13 | 2022-10-19 | 79% | 79% | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 060 | Richard Grayson | 2022-09-26 | 2022-11-06 | 25% | 25% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 068 | Joker | 2022-10-04 | 2022-11-13 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 069 | Joker | 2022-10-05 | 2022-11-12 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 075 | Selina Kyle | 2022-10-11 | 2022-11-14 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 076 | Barbara Gordon | 2022-10-12 | 2022-11-19 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 079 | Barbara Gordon | 2022-10-14 | 2022-11-19 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 088 | Bane | 2022-10-22 | 2022-11-26 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 096 | Barbara Gordon | 2022-11-01 | 2022-12-04 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Design |  |  | 2022-08-01 | 2022-12-06 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 001 | Barbara Gordon | 2022-08-01 | 2022-09-04 | 59% | 59% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 005 | Richard Grayson | 2022-08-05 | 2022-09-12 | 75% | 75% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 006 | Bruce Wayne | 2022-08-06 | 2022-09-16 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 013 | Lucius Fox | 2022-08-09 | 2022-09-13 | 51% | 51% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 039 | Lucius Fox | 2022-09-03 | 2022-10-09 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 041 | Richard Grayson | 2022-09-03 | 2022-10-06 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 047 | James Gordon | 2022-09-10 | 2022-10-13 | 65% | 65% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 050 | Joker | 2022-09-14 | 2022-10-23 | 100% | 100% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 052 | Bruce Wayne | 2022-09-17 | 2022-10-23 | 100% | 100% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 053 | Lucius Fox | 2022-09-19 | 2022-10-24 | 59% | 59% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 057 | Alfred Pennyworth | 2022-09-25 | 2022-11-04 | 62% | 62% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 062 | Bane | 2022-09-30 | 2022-11-08 | 100% | 100% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 064 | Lucius Fox | 2022-10-01 | 2022-11-09 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 071 | Bruce Wayne | 2022-10-07 | 2022-11-12 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 074 | Bane | 2022-10-10 | 2022-11-20 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 077 | Richard Grayson | 2022-10-13 | 2022-11-20 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 081 | Harley Quinn | 2022-10-16 | 2022-11-26 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 082 | Richard Grayson | 2022-10-16 | 2022-11-20 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 091 | Joker | 2022-10-25 | 2022-11-28 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 097 | Lucius Fox | 2022-11-01 | 2022-12-04 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 099 | Barbara Gordon | 2022-11-03 | 2022-12-06 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Development |  |  | 2022-08-07 | 2022-11-27 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 007 | Barbara Gordon | 2022-08-07 | 2022-09-15 | 78% | 78% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 011 | Selina Kyle | 2022-08-08 | 2022-09-18 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 017 | Barbara Gordon | 2022-08-15 | 2022-09-19 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 021 | Alfred Pennyworth | 2022-08-18 | 2022-09-23 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 023 | James Gordon | 2022-08-19 | 2022-09-26 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 031 | Bane | 2022-08-27 | 2022-10-06 | 76% | 76% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 036 | Bane | 2022-08-30 | 2022-10-07 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 045 | Bruce Wayne | 2022-09-08 | 2022-10-14 | 92% | 92% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  | 2022-09-21 | 2022-10-27 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 058 | Selina Kyle | 2022-09-25 | 2022-11-01 | 72% | 72% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 059 | Harley Quinn | 2022-09-25 | 2022-11-01 | 45% | 45% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 063 | Lucius Fox | 2022-09-30 | 2022-11-03 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 065 | Alfred Pennyworth | 2022-10-01 | 2022-11-08 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 070 | James Gordon | 2022-10-05 | 2022-11-08 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 083 | Barbara Gordon | 2022-10-17 | 2022-11-25 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 085 | James Gordon | 2022-10-18 | 2022-11-27 | 0% | 0% | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 086 | Richard Grayson | 2022-10-19 | 2022-11-27 | 0% | 0% | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Requirements |  |  | 2022-08-03 | 2022-12-09 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 003 | Richard Grayson | 2022-08-03 | 2022-09-07 | 62% | 62% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 004 | Selina Kyle | 2022-08-04 | 2022-09-14 | 60% | 60% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 009 | Alfred Pennyworth | 2022-08-07 | 2022-09-11 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 010 | Alfred Pennyworth | 2022-08-08 | 2022-09-13 | 27% | 27% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 014 | Harley Quinn | 2022-08-11 | 2022-09-15 | 95% | 95% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 018 | Harley Quinn | 2022-08-16 | 2022-09-22 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 020 | Alfred Pennyworth | 2022-08-18 | 2022-09-24 | 83% | 83% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 034 | Selina Kyle | 2022-08-29 | 2022-10-06 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 035 | James Gordon | 2022-08-29 | 2022-10-06 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 037 | Richard Grayson | 2022-09-01 | 2022-10-04 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 040 | Lucius Fox | 2022-09-03 | 2022-10-11 | 27% | 27% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 043 | Barbara Gordon | 2022-09-05 | 2022-10-11 | 84% | 84% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 048 | Bruce Wayne | 2022-09-11 | 2022-10-15 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 056 | Joker | 2022-09-25 | 2022-10-29 | 96% | 96% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 061 | James Gordon | 2022-09-28 | 2022-11-03 | 87% | 87% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 067 | Barbara Gordon | 2022-10-02 | 2022-11-10 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 072 | Richard Grayson | 2022-10-07 | 2022-11-13 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 078 | Selina Kyle | 2022-10-13 | 2022-11-22 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 084 | Alfred Pennyworth | 2022-10-18 | 2022-11-26 | 0% | 0% | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 087 | Bane | 2022-10-20 | 2022-11-28 | 0% | 0% | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 090 | Barbara Gordon | 2022-10-23 | 2022-11-28 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 092 | Bane | 2022-10-27 | 2022-12-05 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 093 | James Gordon | 2022-10-29 | 2022-12-02 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 094 | Lucius Fox | 2022-10-30 | 2022-12-03 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 095 | Selina Kyle | 2022-10-31 | 2022-12-08 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 100 | James Gordon | 2022-11-05 | 2022-12-09 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Testing |  |  | 2022-08-07 | 2022-12-09 |  |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 008 | Barbara Gordon | 2022-08-07 | 2022-09-16 | 61% | 61% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 015 | Bane | 2022-08-13 | 2022-09-23 | 70% | 70% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 024 | Lucius Fox | 2022-08-19 | 2022-09-24 | 88% | 88% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 026 | Selina Kyle | 2022-08-23 | 2022-09-30 | 70% | 70% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 029 | Bruce Wayne | 2022-08-25 | 2022-09-30 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 030 | Richard Grayson | 2022-08-27 | 2022-10-04 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 033 | Alfred Pennyworth | 2022-08-29 | 2022-10-04 | 67% | 67% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 042 | James Gordon | 2022-09-03 | 2022-10-09 | 100% | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 046 | Bane | 2022-09-09 | 2022-10-19 | 66% | 66% | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 051 | Alfred Pennyworth | 2022-09-15 | 2022-10-22 | 96% | 96% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 055 | Barbara Gordon | 2022-09-23 | 2022-10-26 | 21% | 21% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 066 | Richard Grayson | 2022-10-02 | 2022-11-06 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 073 | Selina Kyle | 2022-10-09 | 2022-11-17 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 080 | Barbara Gordon | 2022-10-15 | 2022-11-21 | 0% | 0% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 089 | Lucius Fox | 2022-10-23 | 2022-11-26 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| Act 098 | Lucius Fox | 2022-11-01 | 2022-12-09 | 0% | 0% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Progress chart
Project Progress | 100% | 1

## Progress chart ii
Project Progress | 100% | 1
Max | 100%

## Progress Chart iii
Progress | Balance | Dummy
55% | 45% | 1
1
1
1
1
1
1